## Pie Chart
TG TCAR UAT Round 2
Status | Count
Passed | 67
Failed | 70
Not Tested | 407
Under Fix | 8
Ready for Re-test | 53

## DP-A TCAR UAT Summary
DPA TCAR UAT Round2
Tab | Total Test Cases | Passed | Failed | Not Tested | Ready for Re-test | Pass Rate % | Test Rate % | Pending on Rois | Pending on DPA | Rois Owner | Last update date
Definition and Recurrent extent | 8 | 1 | 0 | 7 | 0 | 100% | 12.5% | 0 | 7 | Aspen | 2026-08-14
FRMS | 27 | 0 | 27 | 0 | 18 | 0% | 100% | 0 | 27 | Aska
Rules | 1 | 0 | 0 | 1 | - | - | 0% | 0 | 1 | Aspen
B,X,D | 13 | 0 | 0 | 13 | - | - | 0% | 0 | 13 | Aspen
Split duty | 20 | 0 | 0 | 20 | - | - | 0% | 0 | 20 | Aspen
Limit FT and DP | 13 | 0 | 0 | 13 | - | - | 0% | 0 | 13 | Aspen
RERRP | 14 | 1 | 0 | 13 | - | 100% | 7.14% | 0 | 13 | Aspen
RO | 17 | 0 | 17 | 0 | 16 | 0% | 100% | 1 | 16 | Ninan
RO Cabin | 62 | 40 | 22 | 0 | 15 | 64.5% | 100% | 7 | 15 | Ninan
RO Pilot | 68 | 24 | 4 | 40 | 4 | 85.7% | 41.1% | 0 | 44 | Ninan
Reserve&OFF | 10 | 0 | 0 | 10 | - | - | 0% | 0 | 10 | Aspen
VACATION | 14 | 0 | 0 | 14 | - | - | 0% | 0 | 14 | Aspen
REPORT | 52 | 1 | 0 | 51 | - | 100% | 1.9% | 0 | 51 | Aska
TG910-911(5 LOCAL NIGHT) | 19 | 0 | 0 | 19 | - | - | 0% | 0 | 19 | Aspen
TG491-492 (2 LOCAL NIGHT) | 21 | 0 | 0 | 21 | - | - | 0% | 0 | 21 | Aspen
TRAINING | 12 | 0 | 0 | 12 | - | - | 0% | 0 | 12 | Aspen
Eastward Westward | 2 | 0 | 0 | 2 | - | - | 0% | 0 | 2 | Aspen
TG491-492 (1 LOCAL NIGHT) | 21 | 0 | 0 | 21 | - | - | 0% | 0 | 21 | Aspen
TG910-911(2 LOCAL NIGHT) | 22 | 0 | 0 | 22 | - | - | 0% | 0 | 22 | Aspen
TG910-911(1 LOCAL NIGHT) | 21 | 0 | 0 | 21 | - | - | 0% | 0 | 21 | Aspen
TG517-518(1 LOCAL NIGHT) | 20 | 0 | 0 | 20 | - | - | 0% | 0 | 20 | Aspen
TG517-518(2 LOCAL NIGHT) | 20 | 0 | 0 | 20 | - | - | 0% | 0 | 20 | Aspen
TG658-659(1 LOCAL NIGHT) | 21 | 0 | 0 | 21 | - | - | 0% | 0 | 21 | Aspen
TG020-021-106-107 | 8 | 0 | 0 | 8 | - | - | 0% | 0 | 8 | Aspen
RTAF212 (1 LOCAL NIGHT) | 17 | 0 | 0 | 17 | - | - | 0% | 0 | 17 | Aspen
TG658-659(4 LOCAL NIGHT) | 21 | 0 | 0 | 21 | - | - | 0% | 0 | 21 | Aspen
TOTAL | 544 | 67 | 70 | 407 | 53 | 48.9% | 25.1% | 8 | 469

## Check List
Date / Period | Activity | Reminder / Deliverable | Owner / Focus | Status
By 19 Aug 2026 | Record latest test results | Record latest results for test cases that previously passed but have now failed again, in preparation for the meeting on 20 Aug. | All test owners | Not Started
2026-08-20 | Weekly Meeting - Latest results review | Use the updated latest test-result record as meeting input. | Project team | Not Started
24-28 Aug 2026 | Focus on RO UAT | Everyone should focus on RO UAT while Ninan is onsite. | DPA team | Not Started
2026-08-26 | Publish RO UAT Sep 2026 target | Publish the RO UAT Sep 2026 target so OP-1 can proceed with SWAP testing. | DPA / OP-1 | Not Started
By 28 Aug 2026 | Update RO UAT results | Record the new RO results in the UAT test cases. | DPA team | Not Started
31 Aug-4 Sep 2026 | UAT Oct 2026 pairing and RO execution | Create the UAT Oct 2026 pairing and run RO testing. | DPA team | Not Started
By 4 Sep 2026 | Complete RO result recording | Complete and record all RO results. | DPA team | Not Started
7-11 Sep 2026 | Round 2-3 UAT testing | Focus on testing other UAT areas in Round 2-3 and record all results. | All UAT members | Not Started
By 11 Sep 2026 | Complete Round 2-3 results | Record all Round 2-3 UAT results. | All UAT members | Not Started
2026-09-14 | Publish UAT Oct 2026 schedule | Publish the UAT Oct 2026 schedule. | DP-A team | Not Started
22-24 Sep 2026 | Create UAT Nov 2026 pairing | Create the UAT Nov 2026 pairing. | DPA team | Not Started
25-30 Sep 2026 | RO UAT Nov 2026 and final acceptance | Run RO UAT for Nov 2026. During this period, perform the final check of all rules and RO results. This is the final acceptance checkpoint. | DPA team | Not Started
2026-09-30 | Publish UAT Nov 2027 schedule | Publish the UAT Nov 2027 schedule as stated in the agenda. | DPA team | Not Started
2026-10-01 | Production deployment - TCAR Nov 2026 | Pi team deploys TCAR to production for Nov 2026. DP-A team shifts focus to TCAR production for Nov 2026. | Pi team / DP-A team | Not Started

## Calendar Checklist Overview
2026 - DP-A UAT Calendar
Mon | Tue | Wed | Thu | Fri | Sat | Sun
[5 empty] | 1 | 2 | Aug
3 | 4 | 5 | 6 | 7 | 8 | 9
10 | 11 | 12 | 13 | 14 | 15 | 16
17 | 18 | 19 Deadline: record latest test results | 20 Weekly Meeting: review latest results | 21 | 22 | 23
24 RO UAT focus begins | 25 RO UAT focus | 26 RO UAT focus`nPublish RO UAT Sep target | 27 RO UAT focus Weekly Meeting: review latest results | 28 RO UAT focus`nDeadline: update RO UAT results | 29 | 30
31 Create UAT Oct pairing + run RO
Mon | Tue | Wed | Thu | Fri | Sat | Sun | Sep
| 1 Create UAT Oct pairing + run RO | 2 Create UAT Oct pairing + run RO | 3 Create UAT Oct pairing + run RO | 4 RO execution`nDeadline: record all RO results | 5 | 6
7 Round 2-3 UAT testing | 8 Round 2-3 UAT testing | 9 Round 2-3 UAT testing | 10 Round 2-3 UAT testing | 11 Round 2-3 UAT testing`nDeadline: record all results | 12 | 13
14 Publish UAT Oct 2026 schedule | 15 | 16 | 17 | 18 | 19 | 20
21 | 22 Create UAT Nov 2026 pairing | 23 Create UAT Nov 2026 pairing | 24 Create UAT Nov 2026 pairing | 25 RO UAT Nov + final rules/RO check | 26 RO UAT Nov + final rules/RO check | 27 RO UAT Nov + final rules/RO check
28 RO UAT Nov + final rules/RO check | 29 RO UAT Nov + final rules/RO check | 30 Final acceptance checkpoint`nPublish UAT Nov 2027 schedule
Mon | Tue | Wed | Thu | Fri | Sat | Sun | Oct
|  |  | 1 Production deployment: TCAR Nov 2026 | 2 | 3 | 4
5 | 6 | 7 | 8 | 9 | 10 | 11
12 | 13 | 14 | 15 | 16 | 17 | 18
19 | 20 | 21 | 22 | 23 | 24 | 25
26 | 27 | 28 | 29 | 30 | 31